## Dashboard
Service Weekly KT — Interactive Dashboard
Total Tasks |  | Completed |  | In Process |  | New / Pending | Completion %
Status Breakdown
Status | Count | Share
Done
In process
New
Employee Performance
PIC | Total | Done | In Process | New | Completion %
Ahad
Arslan
Moahed
Moahed - Victory
Victory
Tasks by Module
Module | Total | Done | Open
CC
IT
Qulity
SN
SP
TEC
Weekly Trend — Status Mix & Completion %
Week | Total | Done | In Process | New | Completion %
W19
W21
W23
Weekly Performance by Employee — Completion %
PIC | W19 | W21 | W23
Ahad
Arslan
Moahed
Moahed - Victory
Victory

## Tasks
Open Time | Module | Question | PIC | Management Action | Completion Time | Status | Remarks | Description | New Tasks | Source Week | Done? (✓)
0607 | TEC | Training CC | Ahad | Complete CC Training | Monthly | In process | Plan1/Completed 0) | CC Refreshment Training will be on 22 June. |  | W23 | FALSE
0419 | TEC | Training New model | Ahad | Floor Standing Training Materials update | 2026-04-30 | Done | Training PPT Update in progress. |  | Check with HQ for the training meterial | W19 | TRUE
0426 | TEC | Training Online | Ahad | 1.ABL Service Centers( Including Floor Standing ) 2. | 2026-05-07 | In process | Offline Training 17th May | To be conduct in Jeddah - Arrange food & Claim Take photos | Check for Dammam Staff to come to Riyadh | W19 | FALSE
0503 | TEC | Training Online | Ahad | 1.Training plan for UAE | 2026-05-31 | In process | Offline Training | Conduct Offline training in UAE - Discuss with Hassaib Monday - 4th may |  | W21 | FALSE
0426 | TEC | Installation Training | Ahad | Installtion Training for Sales Dealers Teams in Qassim City. | 2026-04-30 | In process | 0 times / plan 1 times; Communicating with Mr.Alaa for Installation Training in Qassim City in Next week.Instead Training will be done for Riyadh Installation teams. | To be confirmed Next Week |  | W19 | FALSE
0518 | TEC | Technical Support | Ahad | Floor standing unit repair technicial support | 2026-04-30 | Done | 1 / 1 WOs Received | work order:GD20260511315458 has been followed online and closed as value added in Jeddah city. |  | W23 | TRUE
0607 | Qulity | FG Inspection | Ahad | Complete Onsite FG Inspection activity | Monthly | In process | 0 sets / plan 5 sets | will be inspect after New shipment will recieved on 12th june |  | W23 | FALSE
0607 | Qulity | Installation | Ahad | Complete Onsite Installation Inspection activity | Monthly | In process | 0 units / plan 10 units | Installation will be follow up after sales team confirmation. |  | W23 | FALSE
0531 | Qulity | Defective parts | Ahad | Complete Defected Parts Report | Monthly | Done | 24 reported / 28 received | Waiting for 2 PCB ,parts returned which consumed during month of May. | 2 parts on the way 24-May | W23 | TRUE
0419 | SP | SP new modle | Arslan | New Models 2026 SP stock | Monthly | In process | Total Models 55 In Aux Saudi / S.Parts Not available for 33 Models. ordered for 10 models now remaining 23 |  |  | W23 | FALSE
0426 | SP | SP lists | Arslan | 55 models' spare part lists and explored views | 2026-05-30 | In process | 55 Models | full list will all spare parts |  | W21 | FALSE
0419 | SP | SP PO | Arslan | Q1 PO#1 & #2 ready, pending shipment | 2026-04-30 | In process | Shipment is ready for dispatched ETA will updated From HQ |  |  | W21 | FALSE
0419 | SP | SP physical count | Arslan | SP physical count report | Monthly | Done | 10 / 10 Parts |  |  | W23 | TRUE
0419 | SP | SP inventory in SVCs | Arslan | Replenish Safety stock to (Wifex - Classic ) | 2026-04-30 | Done | Done |  |  | W23 | TRUE
0419 | SP | SP Defectives | Arslan | Collect Defected Parts | Monthly | In process | 28 received / 30 Pcs Actual /02 Pics need to collect | 02 remaining to collect emails send to SVC will be collected this week delay beacuse of EID holidays |  | W23 | FALSE
0419 | SP | SP FFR 24H | Arslan | SP Delivery within 24H | Monthly | Done | 29 Delivered / 29 Requets |  |  | W23 | TRUE
0419 | SP | SP Inbound | Arslan | Inbound Feb shipement on GCSS | 2026-04-30 | In process | 4630 inbounded / 4690 received | 30 Pcs PCB for 11222004001632 ODU PCB is remaining | Packing Meterial - need to remove from system & disposal | W23 | FALSE
0426 | SP | SP liquidation | Arslan | package material liquidation | 2026-05-30 | In process | - 26 Parts list ready for approvel - Include new packing meterial list | Send for approvel to Mr. Victory |  | W23 | FALSE
0517 | CC | CC Evalauation | Moahed | CC agents Evaluation report | Monthly | In process | To be shared 7th Jun | To be shared Today |  | W23 | FALSE
0419 | CC | UAE Support | Moahed | Evaluate the perfomance of UAE 3rd Party Call Center agency | 2026-05-04 | Done | Complated - Haseeb shared his ID |  | shift of May to June | W21 | TRUE
0426 | CC | Agent shift | Moahed | CC agents shift in May to June | 2026-05-07 | Done | 25th Jun ~ 15th Jul initially |  |  | W21 | TRUE
0419 | SN | SVC Network | Moahed | Complaete ABL Training on order dispatch and accept | 2026-04-30 | Done | Complated |  |  | W21 | TRUE
0419 | SN | SVC Network | Moahed | Send Test Order to ABL | 2026-04-30 | Done | Complated |  |  | W21 | TRUE
0426 | SN | New ASP | Moahed | 3 New ASP discussion | 2026-06-30 | In process | 1 Shared Contract - 2 Pending | 1 MDM Complated - Waiting other new ASP to share Data | CHeck MDM Account | W23 | FALSE
0503 |  | SVC Network | Moahed | Auto Update for Dashboard | 2026-06-30 | In process | Collect the data from HQ auto to the dashboard | Pending for Meeting with HQ |  | W23 | FALSE
0419 | SN | SVC Network | Moahed | Complate the Warranty payment to ASC | 2026-04-30 | Done | Complated |  |  | W21 | TRUE
0406 | SN | SVC Network | Moahed | Share The warranty Payment slip for Mar | 2026-05-07 | Done | Complated |  |  | W21 | TRUE
0406 | SN | SVC Network | Moahed | Update the ASC Details on GCSS System | 2026-05-07 | Done | Complated |  |  | W21 | TRUE
0406 | SN | SVC Network | Moahed | Start the process of Warranty orders | 2026-06-30 | In process | 3 Payment Uploaded - 1 pending for sharing the invoice ( Wifex ) | Share the confirmed list |  | W23 | FALSE
0511 | SN | WO dispatch | Moahed | Floor standing work order dispatch SVCs, labor price discussion Classic & ZAM WIFIX | 2026-06-30 | Done | One order dispatched and we will pay the same labor fee for now | 1 received |  | W23 | TRUE
0426 | SN | Labor fee | Moahed - Victory | Commerical AC & Floor standing | 2026-06-30 | In process |  | Excel file is ready pending for system update |  | W23 | FALSE
0426 | SN | ASP Settlement | Victory | online payment operation | 2026-05-30 | New | Under checking with IT |  |  | W19 | FALSE
0419 | IT | GCSS system | Victory | GCSS improvement requirements & follow up total18 | Monthly | In process | 6 done / 12 in process Total 18 | Before jun HQ will complate 3 |  | W23 | FALSE
0426 | SN | New ASP | Victory | Sign New contract for HLM | 2026-06-30 | In process | Check with Jon |  |  | W19 | FALSE
0426 | TEC | Training Online | Ahad | 1.ABL Service Centers( Including Floor Standing ) | 2026-05-17 | In process | Offline Training 17th May | To be conduct in Jeddah - Arrange food & Claim Take photos | Dammam Staff came to Riyadh | W21 | FALSE
0426 | TEC | Installation Training | Ahad | Installtion Training for Sales Dealers Teams in Riyadh | 2026-05-31 | In process | 0 times / plan 1 times. | As per Sales team New Installation companies Registration in progress.Hopefully we can conduct Installation Training in Next Week. |  | W21 | FALSE
0511 | SP | SP PO | Arslan | Request GOA replacement request for - AUX19HQCA 1 unit & AUX19CQA 1 unit | 2026-05-11 | Done | Apply in GOA its approved |  |  | W23 | TRUE
0511 | SP | SP inventory in SVCs | Arslan | Supply safety stock for ABL | 2026-06-15 | In process | Safety Stock List is ready will be dispatched after Eid holidays |  |  | W23 | FALSE
0511 | SN | Call Center | Moahed | Check AI agent task and cost | 2026-05-31 | Done | Cost will be 1035 Agent for 5000 Credit | test the lowest version - for after working hours |  | W23 | TRUE
0511 | SN | WO dispatch | Moahed | eXtra Contract Discussion | 2026-05-11 | Done | Share extra feedback on group | share the contract on group |  | W23 | TRUE
0426 | SN | New ASP | Victory | Sign New contract for HMA | 2026-06-30 | In process | under GOA Contract Proccess |  |  | W23 | FALSE
0607 | TEC | Training Online | Ahad | 1.Technical training for SVCs in Jeddah City | 2026-06-18 | In process | Technical Service Training for Floor Standing , RAC ,LCAC Products.Plan1/Completed 0 | Training will be conducted for ZAM and ABL Teams on 18th June,Waiting for Sales team confirmation to finalize Training dates. |  | W23 | FALSE
0607 | TEC | Installation Training | Ahad | Installtion Training for Sales Dealers Teams in Jeddah and Riyadh | 2026/6/31 | In process | InstallationTraining for Floor Standing , RAC ,LCAC Products.Plan1/Completed 1 | Waiting for Jeddah and Riyadh Salesteam Confirmation. |  | W23 | FALSE
0524 | TEC | Training Room | Ahad | Paint training rooms | 2026-06-30 | In process |  |  | New Tasks | W23 | FALSE
0419 | SP | SP PO | Arslan | Total 04 Purchased orders Placed to HQ | 2026-04-30 | In process | Complated : Q1 PO#1 & #2 ready,Approved. pending for shipping - ETA 12th Jun | Pending List - PO3 & PO4 PLaced Approved now waiting for the updated for shipment . |  | W23 | FALSE
0607 | SP | SP Inventorty | Arslan | package material liquidation | 2026-05-30 | In process | - 26 Parts list ready for approvel - Include new packing meterial list | Send for approvel to Mr. Victory |  | W23 | FALSE
0517 | SN | Call Center | Moahed | EID IVR | 2026-05-31 | Done | create the IVR by bevatel |  |  | W23 | TRUE

## How to Use
How to Use This Dashboard
1. Go to the 'Tasks' sheet to edit task data.
2. The 'Status' column has a dropdown — pick Done / In process / New.
3. The 'Done? (✓)' column toggles TRUE/FALSE — TRUE strikes through the row.
4. All KPIs, charts and trend tables on 'Dashboard' update automatically.
5. Use the filter buttons on the Tasks table to slice by PIC, Module, Week, Status.
6. Weekly Trend section compares W19 / W21 / W23 progress side by side.
7. Employee × Week heat matrix shows performance progression per person.
Color legend:
Green = Done Yellow = In process Red = New / Pending